## Team 1 - Report
Team 3: Jenkins Implementation Planning and Progress Tracking (Fixora)
Admin: | Harekrushna Savaliya
Sprint | Task Title | Description | Progress
PREP | Download and Install Java JDK and Jenkins | • Install Java JDK (required for Jenkins) • Install Jenkins (LTS) • Verify Jenkins is running on port 8080 | 100%
PREP | Jenkins Configuration | • Install required plugins: • Pipeline Plugin • Git Plugin • GitHub Integration plugin • Credentials Binding • Create Admin User • Configure Global Security (Role-based Strategy) | 100%
PREP | AWS Jenkins Setup | • Create EC2 instances: Jenkins, Dev, QA (and Prod if needed) • Create Key-Pair • Open required ports (22, 80/443, 8080) • Attach security groups and test SSH | 70%
PREP | Basic Integration on Servers | • Install Git on all servers • Install NodeJS + npm on Dev/QA/Prod • Install PM2 for process management • Install Nginx (reverse proxy) • (Optional) Install Docker on Jenkins server | 0%
PREP | Initial Pipeline Setup | • Create a Jenkins Pipeline job / Multibranch Pipeline • Add first Jenkinsfile (frontend + backend stages) • Run pipeline on Dev to confirm build + deploy works | 10%
S1
S1
S1
S1
S1
S1
S1
S1
S1
S2
S2
S2
S3
S3
S3